## Sheet1
Planned conversions to 8.33 kHz above FL195 - updated in January 2008
Completed conversions to 8.33 kHz (in bold)
| State | ACC Name | SECTOR | Original 25kHz FREQUENCY | TARGET DATE | Converted 8.33kHz FREQUENCY | Convertion | Co-ordinated in | Remarks / Constraints | Update
[5 empty] | For conversion | 8.33kHz | Date | COMT2 Table
[5 empty] | Month / Year | FREQUENCY |  | Date
1 | ALBANIA | Tirana ACC | Tirana Upper | 127.5 | Winter 2009 |  |  |  | as per National Airspace Modernization Programms | 2008-01-25
2 | ALBANIA | Tirana ACC | Tirana Mid | 133.15 | Winter 2009 |  |  |  | as per National Airspace Modernization Programms | 2008-01-25
3 | ALBANIA | Tirana ACC | Tirana all | 131.075 | Winter 2009 |  |  |  | as per National Airspace Modernization Programms | 2008-01-25
4 | BELARUS | Minsk ACC | S1S | 135.075 | 2009 |  |  |  | will be confirmed | 2008-02-05
5 | BELARUS | Minsk ACC | S2W | 124.825 | 2009 |  |  |  | will be confirmed | 2008-02-05
6 | BELARUS | Minsk ACC | S3N | 118.975 | 2009 |  |  |  | will be confirmed | 2008-02-05
7 | BELARUS | Minsk ACC | S4C | 120.125 | 2009 |  |  |  | will be confirmed | 2008-02-05
8 | BELARUS | Minsk ACC | S5W2 | 120.575 | 2009 |  |  |  | will be confirmed | 2008-02-05
9 | BELARUS | Minsk ACC | S6C2 | 119.125 | 2009 |  |  |  | will be confirmed | 2008-02-05
10 | BELARUS | Minsk ACC | S3N+S4C | 120.725 | 2009 |  |  |  | will be confirmed | 2008-02-05
11 | BELARUS | Minsk ACC | S5W2+S2W | 127.625 | 2009 |  |  |  | will be confirmed | 2008-02-05
12 | BELARUS | Minsk ACC | S7S2 | 133.875 | 2009 |  |  |  | will be confirmed | 2008-02-05
13 | BELARUS | Minsk ACC | S8U | 133.55 | 2009 |  |  |  | will be confirmed | 2008-02-05
14 | BELARUS | Minsk ACC | S9U | 131.3 | 2009 |  |  |  | will be confirmed | 2008-02-05
15 | BULGARIA | Sofia ACC | Sofia North Upper | 130.15 | 2008-02-01
16 | BULGARIA | Sofia ACC | Sofia South Upper | 120.775 | 2008-02-01
17 | BULGARIA | Sofia ACC | Sofia West Upper | 128.525 | 2008-02-01
18 | BULGARIA |  | TBC |  | Q4 2008
19 | BULGARIA |  | TBC |  | Q4 2008
20 | BULGARIA |  | TBC |  | Q4 2008
21 | BULGARIA |  | TBC |  | Q4 2008
22 | FRANCE | BORDEAUX ACC | T1 | 123.625 | 2007-10-20 | 123.63 | 2007-10-20 | Yes |  | 2008-01-31
23 | FRANCE | BORDEAUX ACC | H1 | 124.075 | 2007-05-10 | 124.08 | 2007-05-10 | Yes |  | 2008-01-31
24 | FRANCE | BORDEAUX ACC | N1 | 124.825 | In 2008 |  |  |  | Awaiting future sectorisation | 2008-01-31
25 | FRANCE | BORDEAUX ACC | P1 | 132.175 | 2007-05-10 | 132.18 | 2007-05-10 |  |  | 2008-01-31
26 | FRANCE | BORDEAUX ACC | LY | 133.1 | 2007-05-10 | 133.105 | 2007-05-10 |  |  | 2008-01-31
27 | FRANCE | BORDEAUX ACC | X1 | 118.425 | 2008-02-14 |  |  |  | (*) : Due to a retrofit and extension of a radio communication station at Haillan | 2008-01-31
28 | FRANCE | BORDEAUX ACC | RY | 132.425 | 2008-02-14 |  |  |  | (*) : Due to a retrofit and extension of a radio communication station at Haillan | 2008-01-31
29 | FRANCE | BORDEAUX ACC | Z1 | 133.675 | 2008-02-14 |  |  |  | (*) : Due to a retrofit and extension of a radio communication station at Haillan | 2008-01-31
30 | FRANCE | MARSEILLE ACC | B1 | 125.65 | 2007-05-10 | 125.655 | 2007-05-10 |  |  | 2008-01-31
31 | FRANCE | MARSEILLE ACC | M1 | 126.25 | 2007-05-10 | 126.255 | 2007-05-10 |  |  | 2008-01-31
32 | FRANCE | MARSEILLE ACC | K1 | 127.825 | 2007-05-10 | 127.83 | 2007-05-10 |  |  | 2008-01-31
33 | FRANCE | MARSEILLE ACC | A1 | 131 | 2007-05-10 | 131.005 | 2007-05-10 | Yes |  | 2008-01-31
34 | FRANCE | MARSEILLE ACC | F1 | 133.325 | 2007-05-10 | 133.33 | 2007-05-10 | Yes |  | 2008-01-31
35 | FRANCE | MARSEILLE ACC | G1 | 133.425 | 2007-10-25 | 133.43 | 2007-10-25 | Yes |  | 2008-01-31
36 | FRANCE | MARSEILLE ACC | W1 | 134.1 | 2007-05-10 | 134.105 | 2007-05-10 |  |  | 2008-01-31
37 | FRANCE | MARSEILLE ACC | E1 | 135.925 | 2007-05-10 | 135.93 | 2007-05-10 |  |  | 2008-01-31
38 | FRANCE | MARSEILLE ACC | Y1 | 135.4 | 2007-10-25 | 134.405 | 2007-10-25 |  |  | 2008-01-31
39 | FRANCE | PARIS/REIMS ACC | UE | 127.55 | 2007-09-27 | 127.55 | 2007-09-27 |  |  | 2008-01-31
40 | FRANCE | PARIS/REIMS ACC | UF | 132.275 | 2007-09-27 | 132.28 | 2007-09-27 |  |  | 2008-01-31
41 | FRANCE | PARIS/REIMS ACC | UH | 134.4 | 2007-09-27 | 134.405 | 2007-09-27 |  |  | 2008-01-31
42 | FRANCE | PARIS ACC | OG | 127.3 | 2007-05-10 | 127.305 | 2007-05-10 | Yes |  | 2008-01-31
43 | FRANCE | PARIS ACC | UJ | 132.375 | 2007-05-10 | 132.38 | 2007-05-10 |  |  | 2008-01-31
44 | FRANCE | PARIS ACC | UT | 133.5 | 2007-05-10 | 133.505 | 2007-05-10 | Yes |  | 2008-01-31
45 | FRANCE | PARIS ACC | OY | 134.875 | 2007-05-10 | 134.88 | 2007-05-10 |  |  | 2008-01-31
46 | FRANCE | PARIS ACC | UP | 118.225 | 2007-05-10 | 118.23 | 2007-05-10 |  |  | 2008-01-31
47 | FRANCE | PARIS ACC | UZ | 131.25 | 2007-05-10 | 131.255 | 2007-05-10 |  |  | 2008-01-31
48 | FRANCE | PARIS ACC | UK | 129 | Wait of a new radio station |  |  |  | (***) : Due to recent need to enforce coverage, this frequency is now in climax configuration. France wait a new radio station where this frequency will be implemented, and will allow to eliminate the climax. In this configuration, this frequency will be converted to “8.33”. | 2008-01-31
49 | GREECE | ATHINAI ACC | LGGGKFNU | 134.075 | 2008-07-01 |  |  |  | These planned 25 to 8.33 kHz frequency conversions are according to the new sectorization of Athinai & Makedonia ACCs, which will be in operation by the end of 2006. | 2008-01-31
50 | GREECE | ATHINAI ACC | LGGGMILU | 123.825 | 2008-07-01 |  |  |  |  | 2008-01-31
51 | GREECE | MAKEDONIA ACC | LGMDTSLU | 125.35 | 2008-07-01 |  |  |  |  | 2008-01-31
52 | GREECE | MAKEDONIA ACC | LGMDLMOU | 133.875 | 2008-07-01 |  |  |  |  | 2008-01-31
53 | GREECE | MAKEDONIA ACC | LGMDLMOM | 127.475 | 2008-07-01 |  |  |  |  | 2008-01-31
54 | GREECE | ATHINAI ACC | LGGGKRKU | 131325 | 2008-07-01 |  |  |  |  | 2008-01-31
55 | GREECE | MAKEDONIA ACC | LGMDSKPU | 133650 | 2008-07-01 |  |  |  |  | 2008-01-31
56 | IRELAND | SHANNON | ACC/U(U1-3+UEXT) | 135.225 | 2005-09-01 | 135.23 | 2005-09-29 | 2007-10-17 | Successfully converted to 135.230 and satisfactorily evaluated with aircraft by ATC Shannon. | 2008-01-25
57 | IRELAND | SHANNON | ACC/U(U1-3+UEXT) | 120 | Summer 07 | 120.005 | 2007-05-15 | 2007-10-17 | Successfully converted to 120.005 and satisfactorily evaluated with aircraft by ATC Shannon. | 2008-01-25
58 | IRELAND | SHANNON | ACC/U(U1-3+UEXT) | 127.125 | Summer 07 | 127.13 | 2007-05-15 | 2007-10-17 | Successfully converted to 127.130 and satisfactorily evaluated with aircraft by ATC Shannon. | 2008-01-25
59 | IRELAND | SHANNON | ACC/U | 134.275 | 2007-10-09 | 134.28 | 2007-10-09 | 2007-10-17 | Successfully converted to 134.280 and satisfactorily evaluated with aircraft by ATC Shannon. | 2008-01-25
60 | IRELAND | SHANNON | ACC/U | 134.625 | 2007-11-08 | 134.63 | 2007-11-08 |  | Successfully converted to 134.630 and being evaluated. | 2008-01-25
61 | IRELAND | SHANNON | ACC/U | 135.725 | 2007-12-05 | 135.73 | 2007-12-05 |  | Successfully converted to 135.730 and being evaluated. | 2008-01-25
62 | IRELAND | SHANNON | ACC/U | 136.25 | 2008-01-15 | 136.255 | 2008-01-15 |  | Successfully converted to 135.255 and being evaluated. | 2008-01-25
63 | IRELAND | SHANNON | ACC/U | 122.975 | 2008-02-06 | 122.98 | "on target" |  |  | 2008-01-25
64 | ITALY | Milano ACC | CEN | 128.925 MHz | 2008-03-01 |  |  |  | to be confirmed
65 | ITALY | Milano ACC | SES | 130.725 MHz | 2008-03-01 |  |  |  | to be confirmed
66 | ITALY | Milano ACC | SWS | 135.450 MHz | 2008-03-01 |  |  |  | to be confirmed
67 | ITALY | TBC | [6 empty] | to be confirmed
68 | ITALY | TBC | [6 empty] | to be confirmed
69 | PORTUGAL | Lisbon | Upper | 133.9 | 2008-03-01
70 | PORTUGAL | Lisbon | Upper | 134.85 | 2008-03-01
71 | PORTUGAL | Lisbon | Upper | 135.45 | 2008-03-01
72 | ROMANIA | Bucharest | KOMAN TOP | 124.525 | 2007-10-01
73 | SPAIN | MADRID | LECMPAU | 132050 | 2008-07-03
74 | SPAIN | MADRID | LECMTER | 119625 | 2008-07-03
75 | SPAIN | BARCELONA | LECBCCC | 135350 | 2008-07-03
76 | SPAIN | BARCELONA | LECBVNL | 133075 | 2008-07-03
77 | SWEDEN | Malmö | 2 | 127.75 | 2008-03-13 |  |  |  | Conditioned UHF licens. | 2008-01-28
78 | SWEDEN | Malmö | 9 | 135.8 | 2008-03-13 |  |  |  | Conditioned UHF lic. | 2008-01-28
79 | SWEDEN | Malmö | 4 | 124.4 | 2008-05-08 |  |  |  | Conditioned UHF lic. | 2008-01-28
80 | SWEDEN | Malmö | 6 | 128.05 | 2008-05-08 |  |  |  | Conditioned UHF lic. | 2008-01-28
81 | SWEDEN | Malmö | W | 136.3 | 2008-06-05 |  |  |  | Conditioned UHF lic./Note.136,300 converts to 133,260 | 2008-01-28
82 | SWEDEN | Malmö | Y | 134.45 | 2008-06-05 |  |  |  | Note.New sector since 2006-06-08 | 2008-01-28
83 | UK | LACC | S12 | 133.45 | 2008-07-01 |  |  |  |  | 2008-01-29
84 | UK | LACC | S14 | 118.475 | 2008-07-01 |  |  |  |  | 2008-01-29
85 | UK | LACC | S16 | 134.45 | 2008-07-01 |  |  |  |  | 2008-01-29
86 | UK | LACC | S25 | 132.45 | 2008-07-01 |  |  |  |  | 2008-01-29
87 | UK | LACC | S26 | 132.6 | 2008-07-01 |  |  |  |  | 2008-01-29
88 | UK | LACC | S27 | 129.2 | 2008-07-01 |  |  |  |  | 2008-01-29
89 | UK | LACC | S28 | 127.1 | 2008-07-01 |  |  |  |  | 2008-01-29
90 | UK | LACC | S32 | 131.125 | 2008-07-01 |  |  |  |  | 2008-01-29
91 | UK | MACC | S29 | 118.775 | 2010-03-01 |  |  |  | Dependency on move of MACC to new centre at Prestwick | 2008-01-29